## Methodology
Tasman Mutual Bank — CIRMP All-Hazards Risk Register
Document 2 ¦ Methodology & scoring ¦ Scenario-based portfolio artefact (fictional entity)
Purpose
This register identifies and rates material risks to TMB’s payment-systems / core-banking asset across the four CIRMP hazard vectors. Risks are scored before and after controls (inherent vs residual) on a 5×5 matrix, with treatments mapped to a 30/90/180-day remediation horizon. The methodology is harmonised with ISO 31000 and APRA CPS 230 operational-risk practice.
Likelihood scale (1–5)
Score | Rating | Descriptor
1 | Rare | May occur only in exceptional circumstances (< once in 5 years)
2 | Unlikely | Could occur but not expected (within 2–5 years)
3 | Possible | Might occur at some point (within 1–2 years)
4 | Likely | Will probably occur in most circumstances (within 12 months)
5 | Almost certain | Expected to occur in most circumstances (multiple times a year)
Impact scale (1–5)
Score | Rating | Descriptor (member / operational / regulatory)
1 | Insignificant | Negligible disruption; no member harm; no reportable event
2 | Minor | Short, contained disruption; minimal member impact; internal only
3 | Moderate | Noticeable disruption to a critical operation; some member impact; possible regulator notification
4 | Major | Critical operation breaches tolerance; widespread member harm; mandatory incident notification
5 | Severe | Sustained loss of a critical operation; systemic member harm; significant regulatory / reputational consequence
Risk rating bands (Likelihood × Impact)
Score range | Rating | Required action
16 – 25 | Critical | Board-level escalation; immediate treatment; track to closure
10 – 15 | High | Senior management ownership; treat within 90 days
5 – 9 | Medium | Manage by routine controls; treat within 180 days
1 – 4 | Low | Accept / monitor; review at next cycle
CIRMP hazard vectors
Vector | CIRMP Rules | What it covers
Cyber & information security | s8 | Threats to the confidentiality, integrity or availability of the asset’s ICT and data (ransomware, intrusion, data breach)
Personnel | s9 | Trusted-insider, screening, key-person and people-driven risks to the asset
Supply chain | s10 | Risks arising from material service providers, concentration, nth-party dependencies and FOCI
Physical & natural | s11 | Physical security of sites and natural-hazard / environmental threats to the asset
Control effectiveness: Effective = controls reliably reduce the risk ¦ Partial = controls exist but have gaps ¦ Ineffective = controls absent or not operating.
Note: TMB is fictional. Ratings and timelines are illustrative of a realistic mid-tier ADI, not measurements of a real entity.

## Risk Register
Tasman Mutual Bank — CIRMP All-Hazards Risk Register
Document 2 ¦ Risk register ¦ Inherent → residual scoring across the four hazard vectors
Risk ID | Hazard Vector | Risk Title | Risk Description (cause → event → consequence) | Affected Critical Operation | CIRMP Rule | Inh. L | Inh. I | Inh. Score | Inh. Rating | Key Existing Controls | Control Effect. | Res. L | Res. I | Res. Score | Res. Rating | Treatment / Remediation | Risk Owner | Target | Status
CYB-01 | Cyber & information security | Ransomware on core banking / payments platform | Phishing or exploited edge service → ransomware encrypts core platform → sustained loss of payments and deposit access. | Payments and settlement | s8 | 4 | 5 | 20 | Critical | EDR on endpoints; immutable offline backups; network segmentation; Essential Eight ML-1 baseline. | Partial | 2 | 5 | 10 | High | Uplift Essential Eight to ML-2; test isolated recovery to tolerance; segment payments zone. | CISO | 90 days | In Progress
CYB-02 | Cyber & information security | Privileged credential compromise | Inconsistent MFA on legacy admin paths → stolen privileged credentials → unauthorised access to the asset. | Card authorisation and processing | s8 | 4 | 4 | 16 | Critical | Phishing-resistant MFA on most systems; PAM partially deployed; access reviews. | Partial | 2 | 4 | 8 | Medium | Enforce MFA on all admin access; complete PAM rollout; just-in-time privilege. | CISO | 30 days | In Progress
CYB-03 | Cyber & information security | Unpatched internet-facing systems | Patch cadence gaps on internet-facing systems → known vulnerability exploited → data breach and NDB exposure. | Internet and mobile banking | s8 | 3 | 4 | 12 | High | Monthly patch cycle; quarterly vulnerability scanning; WAF. | Partial | 2 | 4 | 8 | Medium | 48-hour patch SLA for internet-facing systems; align to Essential Eight ML-2 patching. | Head of Security Operations | 90 days | In Progress
CYB-04 | Cyber & information security | DDoS on digital banking channels | Volumetric or application-layer DDoS → degradation of internet/mobile banking → loss of member access. | Internet and mobile banking | s8 | 3 | 3 | 9 | Medium | CDN with DDoS scrubbing; rate limiting; upstream provider mitigation. | Effective | 2 | 3 | 6 | Medium | Validate failover and scrubbing capacity; run a DDoS scenario test. | Head of Infrastructure | 180 days | Monitoring
SUP-01 | Supply chain | Cloud concentration risk | Core platform hosted with a single cloud provider → provider-wide outage → cascading loss of critical operations. | Payments and settlement | s10 | 3 | 5 | 15 | High | Single CSP with multi-AZ; DR region configured; CPS 230 service agreement. | Partial | 2 | 5 | 10 | High | Document exit / portability plan; strengthen MSP agreement; test cross-region recovery. | Head of Third-Party Risk | 180 days | Open
SUP-02 | Supply chain | Material payments processor failure | Failure or insolvency of a material payments processor → inability to clear / settle → settlement disruption. | Payments and settlement | s10 | 2 | 5 | 10 | High | SLA and KPI monitoring; financial-viability checks at onboarding. | Partial | 2 | 4 | 8 | Medium | Build BCP for processor outage; assess alternate provider; add step-in / continuity clauses. | Head of Payments | 90 days | Open
SUP-03 | Supply chain | Fourth-party (nth-party) dependency opacity | Limited visibility of material subcontractors behind key providers → unseen downstream failure → untracked exposure. | Fraud detection and transaction monitoring | s10 | 3 | 4 | 12 | High | Primary-vendor due diligence; limited nth-party mapping. | Ineffective | 2 | 4 | 8 | Medium | Map material subcontractors per CPS 230; require subcontractor-disclosure clauses; supply-chain vulnerability mapping per draft CIRMP rules. | Head of Third-Party Risk | 180 days | Open
SUP-04 | Supply chain | Vendor of concern (FOCI) & overseas processing | Foreign ownership/control/influence in a key software supplier, plus overseas storage of sensitive operational information → interference / data-sovereignty risk. | Card authorisation and processing | s10 | 3 | 4 | 12 | High | Contractual security clauses; partial data-residency controls. | Partial | 2 | 4 | 8 | Medium | Conduct FOCI assessment of key suppliers; restrict overseas storage of sensitive operational information; align to draft CIRMP FOCI rules. | Head of Third-Party Risk | 180 days | Open
PER-01 | Personnel | Trusted-insider data exfiltration | Privileged employee with broad access → deliberate exfiltration of member data → large-scale privacy breach. | Deposit-taking and account access | s9 | 3 | 5 | 15 | High | Partial DLP; periodic access reviews; logging. | Partial | 2 | 4 | 8 | Medium | Uplift DLP coverage; enforce least privilege; deploy user-behaviour analytics (UEBA). | CISO / CHRO | 90 days | In Progress
PER-02 | Personnel | Background screening gaps for trusted roles | Pre-employment checks only, no periodic re-screening → undetected change in trusted-person risk → insider compromise. | Payments and settlement | s9 | 3 | 4 | 12 | High | Pre-employment police / identity checks; role-based access. | Partial | 2 | 4 | 8 | Medium | Establish a personnel security plan; periodic re-screening for trusted roles; prepare for AusCheck-style background checking. | CHRO | 90 days | Open
PER-03 | Personnel | Key-person dependency in payments operations | Critical payments knowledge concentrated in a few individuals → unplanned departure / absence → inability to operate or recover. | Payments and settlement | s9 | 4 | 3 | 12 | High | Some documented runbooks; partial cross-skilling. | Partial | 2 | 3 | 6 | Medium | Cross-train; complete operational runbooks; define succession for key roles. | Head of Payments Operations | 180 days | Open
PER-04 | Personnel | Staff phishing / social engineering | Targeted phishing or social engineering of staff → credential or session compromise → foothold into the asset. | Internet and mobile banking | s9 | 4 | 4 | 16 | Critical | Security awareness training; email filtering; MFA. | Partial | 3 | 3 | 9 | Medium | Run recurring phishing simulations; deploy phishing-resistant (FIDO2) MFA; tighten help-desk verification. | CISO | 90 days | In Progress
PHY-01 | Physical & natural | Primary data centre power / flood outage | Power failure or flooding at the primary data centre → loss of processing capability → outage of critical operations. | Payments and settlement | s11 | 2 | 5 | 10 | High | UPS and standby generator; environmental monitoring; DR site. | Effective | 1 | 5 | 5 | Medium | Test DR failover to tolerance; validate fuel / power endurance; review site flood rating. | Head of Infrastructure | 180 days | Monitoring
PHY-02 | Physical & natural | Unauthorised physical access to facilities | Weak physical access control to data centre / comms rooms → unauthorised entry → tampering or theft of equipment. | Card authorisation and processing | s11 | 2 | 4 | 8 | Medium | Badge access; CCTV; visitor sign-in. | Effective | 1 | 4 | 4 | Low | Quarterly physical-access reviews; tighten visitor escorting; central physical-security register. | Head of Facilities | 180 days | Monitoring
PHY-03 | Physical & natural | Natural hazard affecting Sydney HQ / site | Flood, storm or bushfire affecting Sydney HQ and primary site → site inaccessibility → disruption to operations and staff. | Fraud detection and transaction monitoring | s11 | 2 | 4 | 8 | Medium | Business continuity plan; remote-work capability. | Partial | 2 | 3 | 6 | Medium | Scenario-test extreme-but-plausible events (CPS 230); confirm geo-separated recovery site. | Head of Operational Resilience | 180 days | Open
PHY-04 | Physical & natural | Concurrent loss of primary and secondary sites | Insufficient geographic separation between sites → a single regional event disables both → inability to recover within tolerance. | Payments and settlement | s11 | 2 | 5 | 10 | High | Two operating sites; separation distance unverified. | Partial | 1 | 5 | 5 | Medium | Verify geographic separation; define recovery-time tolerance; conduct a dual-site loss test. | Head of Operational Resilience | 180 days | Open

## Summary Dashboard
Tasman Mutual Bank — CIRMP Risk Profile Summary
Document 2 ¦ Auto-calculated from the Risk Register tab
Risks by hazard vector
Category | Count
Cyber & information security | 4
Personnel | 4
Supply chain | 4
Physical & natural | 4
Total | 16
Inherent risk distribution
Category | Count
Critical | 3
High | 10
Medium | 3
Low | 0
Total | 16
Residual risk distribution
Category | Count
Critical | 0
High | 2
Medium | 13
Low | 1
Total | 16
Residual High + Critical (priority backlog) | 2
Read this register alongside the four hazard-module documents and the CPS 230 supply-chain cross-map.