TASMAN MUTUAL BANK

Annual Critical Infrastructure Risk Management Program Report

Document 7  |  Financial year ended 30 June 2026  |  Submitted to the Reserve Bank of Australia

# 1. Board attestation

The Board of Tasman Mutual Bank, as the accountable authority for the critical infrastructure asset, has reviewed and approved this annual report for the financial year ended 30 June 2026. Based on the assurance provided to it, the Board attests that: - the Critical Infrastructure Risk Management Program was up to date as at the end of the reporting period; and - the program operated to identify and manage material risks to the asset during the period, subject to the material variations and remediation set out in section 6 — most significantly, the planned uplift of Essential Eight maturity to the required level. This report is submitted to the Reserve Bank of Australia within 90 days of the end of the financial year.

| Approved by | Name | Signature | Date |
| --- | --- | --- | --- |
| Board Chair |  |  |  |
| Chief Executive Officer |  |  |  |
| Chief Risk Officer |  |  |  |

# 2. Executive summary

During FY2025-26, TMB established and operated an all-hazards CIRMP for its core banking and payments asset, harmonised with APRA CPS 230. No hazard had a significant relevant impact on the asset during the period. The annual assessment identified sixteen material risks across the four hazard vectors, of which two carry a residual High rating — ransomware exposure to the core platform and concentration on a single cloud provider. The most significant program gap is cyber maturity: assessed against the Essential Eight, TMB’s overall maturity is currently below the required ML-1 floor, and a funded uplift to ML-2 is underway. All material risks are under active treatment against a 30/90/180-day roadmap, overseen by the Board Risk Committee.

# 3. Executive dashboard

## 3.1 Material risk profile by hazard vector

| Hazard vector | Risks | Highest residual |
| --- | --- | --- |
| Cyber & information security | 4 | High |
| Supply chain | 4 | High |
| Personnel | 4 | Medium |
| Physical & natural | 4 | Medium |
| Total | 16 | — |

## 3.2 Residual risk distribution

| Rating | Critical | High | Medium | Low |
| --- | --- | --- | --- | --- |
| Count | 0 | 2 | 13 | 1 |

For comparison, the inherent profile (before controls) was three Critical and nine High; controls bring all but two risks to Medium or Low residual.

## 3.3 Essential Eight maturity snapshot

| Measure | Status |
| --- | --- |
| Overall current maturity (lowest common level) | ML-0 |
| CIRMP obligation (floor) | ML-1 |
| Forward target (draft amendments) | ML-2 |
| Strategies at or above ML-1 | 6 of 8 |
| Strategies at or above ML-2 | 1 of 8 |

## 3.4 Remediation status

| Horizon | Focus | Status |
| --- | --- | --- |
| 30 days | Phishing-resistant MFA; enforce admin MFA | In progress |
| 90 days | Patching SLAs; PAM; macro & OS hardening; DLP; screening plan | In progress |
| 180 days | Application control; cloud exit plan; nth-party mapping; site separation | Open |

# 4. Program status and effectiveness

The program was up to date at the end of the reporting period: scope, governance, the risk register and all four hazard modules were current. It was effective in establishing all-hazards risk management and in reducing inherent exposure, but it was not yet fully effective against the cyber framework obligation, where overall Essential Eight maturity sits below ML-1. This is the principal driver of the qualified attestation in section 1 and the focus of the uplift in section 6.

# 5. Material hazards with significant impact during the period

No cyber, personnel, supply-chain or physical/natural hazard had a significant relevant impact on the availability, integrity, reliability or confidentiality of the asset during FY2025-26. No critical cyber security incidents were reportable to the Australian Signals Directorate during the period. Lower-severity events were managed within tolerance and fed into the risk register.

# 6. Material variations and planned uplift

The following material variations and planned improvements were identified and are tracked to closure:

- Cyber maturity: uplift the Essential Eight from an overall ML-0 to ML-2 across all eight strategies, prioritising application control and user application hardening (currently ML-0).

- Supply chain: complete cloud exit / portability planning and fourth-party mapping; conduct FOCI and overseas-processing assessments for flagged providers.

- Personnel: introduce a personnel security plan with periodic re-screening, moving toward AusCheck-style background checking.

- Physical & natural: verify geographic separation between the primary and recovery sites and define recovery-time tolerances.

# 7. Conclusion

TMB has a current, board-governed, all-hazards CIRMP harmonised with CPS 230. The control environment materially reduces inherent risk, and the residual profile is concentrated in two High risks and a known cyber-maturity gap, all under funded remediation. The Board will review progress quarterly and re-attest at the end of FY2026-27.